## Burndown
Sprint | Day | Calendar Date | Ideal Remaining Points | Actual Remaining Points | Story Points Completed Today | Sprint Notes
Sprint 1 | Day 01 | 2026-03-01 | 36 | 36 | 0 | Sprint 1 Kickoff: Architecture setup & DB models
Sprint 1 | Day 02 | 2026-03-02 | 32.4 | 34 | 2 | User registration and password hashing completed
Sprint 1 | Day 03 | 2026-03-03 | 28.8 | 30 | 4 | JWT authentication and sliding refresh merged
Sprint 1 | Day 04 | 2026-03-04 | 25.2 | 26 | 4 | TOTP multi-factor authentication setup
Sprint 1 | Day 05 | 2026-03-05 | 21.6 | 21 | 5 | MFA verify and rate limiter merged ahead of schedule
Sprint 1 | Day 06 | 2026-03-06 | 18 | 18 | 3 | 6-stage upload pipeline initial magic byte scan
Sprint 1 | Day 07 | 2026-03-07 | 14.4 | 13 | 5 | ClamAV daemon connector integration
Sprint 1 | Day 08 | 2026-03-08 | 10.8 | 9 | 4 | EICAR detection and quarantine folder isolation
Sprint 1 | Day 09 | 2026-03-09 | 7.2 | 5 | 4 | Admin quarantine release/purge endpoints
Sprint 1 | Day 10 | 2026-03-10 | 0 | 0 | 5 | Sprint 1 Review: 36/36 points delivered cleanly
Sprint 2 | Day 01 | 2026-03-15 | 38 | 38 | 0 | Sprint 2 Kickoff: Cryptography and access control
Sprint 2 | Day 02 | 2026-03-16 | 34.2 | 35 | 3 | AES-256-GCM envelope encryption primitives
Sprint 2 | Day 03 | 2026-03-17 | 30.4 | 30 | 5 | Decryption streaming download service
Sprint 2 | Day 04 | 2026-03-18 | 26.6 | 26 | 4 | Folder hierarchy and BOLA prevention
Sprint 2 | Day 05 | 2026-03-19 | 22.8 | 20 | 6 | DAC granular permissions (VIEWER, DOWNLOADER, etc.)
Sprint 2 | Day 06 | 2026-03-20 | 19 | 16 | 4 | Public share link engine with 32-byte tokens
Sprint 2 | Day 07 | 2026-03-21 | 15.2 | 12 | 4 | Expiring link password protection & download limits
Sprint 2 | Day 08 | 2026-03-22 | 11.4 | 8 | 4 | SHA-256 tamper-evident audit logging blockchain
Sprint 2 | Day 09 | 2026-03-23 | 7.6 | 4 | 4 | Continuous audit log integrity verifier API
Sprint 2 | Day 10 | 2026-03-24 | 0 | 0 | 4 | Sprint 2 Review: 38/38 points delivered cleanly
Sprint 3 | Day 01 | 2026-03-29 | 40 | 40 | 0 | Sprint 3 Kickoff: DevSecOps CI/CD & Frontend UI
Sprint 3 | Day 02 | 2026-03-30 | 36 | 36 | 4 | React Vite TypeScript app shell & AuthContext
Sprint 3 | Day 03 | 2026-03-31 | 32 | 31 | 5 | User dashboard, upload, and file browser views
Sprint 3 | Day 04 | 2026-04-01 | 28 | 26 | 5 | Admin SOC dashboard, quarantine, and audit UI
Sprint 3 | Day 05 | 2026-04-02 | 24 | 21 | 5 | GitHub Actions 14-stage DevSecOps pipeline setup
Sprint 3 | Day 06 | 2026-04-03 | 20 | 17 | 4 | Bandit, Safety, TruffleHog automated security gates
Sprint 3 | Day 07 | 2026-04-04 | 16 | 12 | 5 | Kubernetes production manifests & container sandboxing
Sprint 3 | Day 08 | 2026-04-05 | 12 | 8 | 4 | OWASP ZAP baseline scan integration & zap-config
Sprint 3 | Day 09 | 2026-04-06 | 8 | 3 | 5 | Fuzz testing suite implementation and execution
Sprint 3 | Day 10 | 2026-04-07 | 0 | 0 | 3 | Sprint 3 Review: Final capstone delivery complete