## Backlog
Issue Key | Issue Type | Summary / User Story | Epic Link | Story Points | Priority | Sprint Assignment | Status | Assignee | Acceptance Criteria
SEC-01 | Story | Implement Argon2id user password hashing with salt | Authentication | 5 | Highest | Sprint 1 | Done | Rahul Kumar | Passwords hashed with m=64MB, t=3, p=4. Plaintext never stored.
SEC-02 | Story | Build JWT authentication with sliding token refresh | Authentication | 5 | Highest | Sprint 1 | Done | Rahul Kumar | Tokens expire in 60m. Valid signature required.
SEC-03 | Story | Implement TOTP Multi-Factor Authentication with QR codes | Authentication | 5 | High | Sprint 1 | Done | Rahul Kumar | RFC 6238 compliance, 30s window, invalid codes rejected.
SEC-04 | Story | Create multi-stage file upload with MIME magic detection | Threat Scanning | 8 | Highest | Sprint 1 | Done | Priya Sharma | libmagic MIME inspection rejects spoofed extensions.
SEC-05 | Story | Integrate ClamAV daemon malware detection scanner | Threat Scanning | 8 | Highest | Sprint 1 | Done | Priya Sharma | EICAR test string automatically identified as malware.
SEC-06 | Story | Build file quarantine isolation and admin purge API | Threat Scanning | 5 | High | Sprint 1 | Done | Priya Sharma | Infected files moved to /quarantine; download returns 403.
SEC-07 | Story | Develop AES-256-GCM envelope encryption service | Cryptography | 8 | Highest | Sprint 2 | Done | Rahul Kumar | Files encrypted at rest with unique 96-bit nonce & 128-bit tag.
SEC-08 | Story | Implement streaming decryption on authorized download | Cryptography | 5 | High | Sprint 2 | Done | Rahul Kumar | Decrypt on the fly without intermediate plaintext temp files.
SEC-09 | Story | Build folder hierarchy management with BOLA guard | Access Control | 5 | High | Sprint 2 | Done | Arjun Rao | User cannot access or delete folders belonging to other users.
SEC-10 | Story | Implement granular user-to-user permission sharing | Access Control | 5 | High | Sprint 2 | Done | Arjun Rao | VIEWER, DOWNLOADER, EDITOR permissions strictly enforced.
SEC-11 | Story | Build expiring public share links with password protection | Access Control | 5 | High | Sprint 2 | Done | Arjun Rao | 32-byte token, expiry timestamp, download limit decrementing.
SEC-12 | Story | Implement tamper-evident SHA-256 audit log blockchain | Audit & SOC | 8 | Highest | Sprint 2 | Done | Sushmitha Reddy | Each log entry stores hash(prev_hash + log_data). Gap detection works.
SEC-13 | Story | Build SOC Admin Dashboard with quarantine & audit view | Audit & SOC | 5 | High | Sprint 3 | Done | Sushmitha Reddy | Admin can view stats, audit logs, quarantine, and pipeline status.
SEC-14 | Story | Design modern React Tailwind frontend with glassmorphism | Frontend UI | 8 | High | Sprint 3 | Done | Arjun Rao | Clean accessible UI with Dark/Light styling and responsive cards.
SEC-15 | Story | Implement CI/CD GitHub Actions DevSecOps security gate | DevSecOps | 8 | Highest | Sprint 3 | Done | Priya Sharma | Bandit, Safety, TruffleHog, and pytest run on every pull request.
SEC-16 | Task | Configure Kubernetes manifests with non-root securityContext | Deployment | 5 | Medium | Sprint 3 | Done | Priya Sharma | K8s deployments for frontend, backend, postgres, and clamav.
SEC-17 | Task | Conduct OWASP ZAP automated baseline security scan | Security Validation | 5 | High | Sprint 3 | Done | Priya Sharma | Zero High or Medium alerts in authenticated ZAP baseline scan.
SEC-18 | Task | Develop comprehensive security fuzz testing suite | Security Validation | 5 | High | Sprint 3 | Done | Priya Sharma | Auth and upload endpoints tested against 500+ malformed payloads.