## Risk_Register
Risk ID | Threat Ref | Vuln Ref | Risk Description | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Score | Inherent Level | Security Controls Applied | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Score | Residual Level | Treatment Strategy | Action Plan | Risk Owner
RSK-01 | S-01 | V-04 | Credential brute forcing leading to unauthorized account takeover | 4 | 4 |  | High | SC-01, SC-15 (Argon2id, Lockout, Rate Limiting) | 1 | 3 |  | Low | Mitigate | Active monitoring of login failures via SOC | Rahul Kumar
RSK-02 | I-02 | V-01 | BOLA access control failure allowing external download of private files | 4 | 5 |  | Critical | SC-10 (Strict ownership query verification) | 1 | 4 |  | Low | Mitigate | Continuous automated regression tests in CI | Rahul Kumar
RSK-03 | T-01 | V-02 | Malicious file upload infecting server host or client downloaders | 4 | 5 |  | Critical | SC-04, SC-05, SC-06 (6-Stage Scan + Quarantine) | 1 | 4 |  | Low | Mitigate | Weekly signature update for ClamAV engine | Priya Sharma
RSK-04 | T-01 | V-05 | Ciphertext tampering or data leakage via crypto implementation flaw | 3 | 5 |  | High | SC-07 (AES-256-GCM + unique 96-bit IV) | 1 | 4 |  | Low | Mitigate | FIPS-compliant cryptography audits | Rahul Kumar
RSK-05 | T-02 | V-07 | Audit log modification by rogue admin to hide insider threat | 2 | 4 |  | Medium | SC-12 (SHA-256 cryptographically chained ledger) | 1 | 2 |  | Low | Mitigate | Automated daily blockchain ledger verification | Sushmitha Reddy
RSK-06 | D-01 | V-03 | Zip bomb or volumetric attack exhausting server storage space | 4 | 4 |  | High | SC-04 (50MB hard limit + zip ratio detection) | 1 | 2 |  | Low | Mitigate | Disk threshold alert at 80% capacity | Priya Sharma
RSK-07 | E-01 | V-11 | Privilege escalation by regular user modifying roles | 3 | 5 |  | High | SC-10 (RBAC enforcement in middleware) | 1 | 3 |  | Low | Mitigate | Role change notifications sent to Auditor | Rahul Kumar
RSK-08 | I-01 | V-10 | Exposure of backend secrets or keys in CI/CD build artifacts | 3 | 4 |  | High | SC-14 (Secret scanning with TruffleHog in CI) | 1 | 2 |  | Low | Mitigate | Pre-commit hooks enforcing local scanning | Priya Sharma

## Risk_Heat_Map
SecureShare 5x5 Cyber Risk Assessment Heat Map
Impact \ Likelihood | 1 - Rare | 2 - Unlikely | 3 - Moderate | 4 - Likely | 5 - Almost Certain
5 - Catastrophic | 5 (Low) [RSK-04*] | 10 (Med) | 15 (High) | 20 (Critical) [RSK-02,03] | 25 (Critical)
4 - Major | 4 (Low) [RSK-02*] | 8 (Med) [RSK-05] | 12 (High) [RSK-07,08] | 16 (High) [RSK-01,06] | 20 (Critical)
3 - Moderate | 3 (Low) [RSK-01*,07*] | 6 (Med) | 9 (Med) | 12 (High) | 15 (High)
2 - Minor | 2 (Low) [RSK-05*,06*,08*] | 4 (Low) | 6 (Med) | 8 (Med) | 10 (Med)
1 - Insignificant | 1 (Low) | 2 (Low) | 3 (Low) | 4 (Low) | 5 (Low)
Note: [RSK-XX] denotes Inherent Risk location. [RSK-XX*] denotes Post-Treatment Residual Risk location.